WEEK 1 IGNITION PLAN — NBCA WORKFORCE PIPELINE

Built specifically for: NBCA office as dispatch base | 2 contractors ready | Team: You, Idris, Keymon | App-first approach.

SITUATION: You have contractors ready. You have a location. You have a team. The only thing missing is execution. This plan eliminates every excuse. Run it exactly as written.

YOUR STARTING CONDITIONS (CONFIRMED)

| CONDITION | STATUS | ACTION NEEDED |
| --- | --- | --- |
| Dispatch location | ✅ READY | NBCA office — brief Idris on check-in setup today |
| Contractors (1–2 ready) | ✅ READY | Call both TODAY — get Job Request Forms filled before Day 1 |
| Team assigned | ✅ READY | Share Doc 24 with Idris and Keymon before Day 1 |
| Documents (23 docs) | ✅ READY | Print Day 1 essentials — see checklist below |
| Trade focus | ✅ READY | Carpentry / framing / demo — recruit this specifically |
| App / Supabase | 🔄 BUILDING | Use Google Sheets until app is live — do not wait |
| Worker roster | ⚠️ BUILD NOW | Need 8–12 workers signed up before Day 1 dispatch |
| Worker broadcast list | ⚠️ BUILD NOW | Group text or WhatsApp — set up before Day 1 |

PRE-LAUNCH (NIGHT BEFORE DAY 1)

Complete every item below before you sleep. Day 1 starts at 5:45 AM — there is no time to set up in the morning.

YOU:

- Call both ready contractors — confirm job details, get Job Request Form filled

- Confirm start time, site address, # workers needed, trade needed (carpentry/demo)

- Text workers: 'NBCA Workforce launching [DATE]. Gather at [NBCA OFFICE ADDRESS] by 6:00 AM. Reply YES if available.'

- Count replies — if fewer than job slots, call more workers tonight

- Brief Idris: how many jobs tomorrow, what trades, how many workers expected

KEYMON:

- Set up Google Sheet: Workers tab with all current worker names entered

- Print 10 copies of: Worker Intake Form, Expectation Agreement, Safety Acknowledgment

- Print 2 copies of: Daily Check-In Sheet, Dispatch Board

- Prepare Worker ID card sheet — ready to fill and issue

IDRIS:

- Set up check-in table at NBCA office — table, chairs, forms, pens

- Review Doc 06 (Dispatch SOP) tonight — know the morning flow cold

- Have dispatcher phone charged and broadcast list ready

✓  If both contractors are confirmed and 5+ workers replied YES — you are GO for Day 1.

| DAY 1 Monday | THEME: FIRST DISPATCH — PROVE THE SYSTEM WORKS |
| --- | --- |

| WHO | TIME | TASK |
| --- | --- | --- |
| IDRIS | 5:45 AM | Arrive NBCA office. Set up check-in table. Have forms ready. |
| YOU | 5:50 AM | Arrive. Confirm job details one more time with both contractors. |
| IDRIS | 6:00 AM | Workers begin arriving. Check each one in on the sheet. |
| KEYMON | 6:15 AM | Arrive. Collect any unsigned forms from workers. Enter names in Google Sheet. |
| IDRIS | 6:30 AM | Begin assignments. Carpentry/demo workers to confirmed job(s). Use skill level to match. |
| YOU | 6:45 AM | Send contractor confirmation text: workers assigned, en route, ETA. |
| IDRIS | 7:00 AM | Dispatch assigned workers. Give each: site address, supervisor name, start time. |
| IDRIS | 7:15 AM | Manage standbys. Keep group calm. Do NOT let idle group grow past 8 AM. |
| IDRIS | 8:00 AM | Release all unplaced workers. Script: 'No work today. Stay available. We'll call tomorrow.' |
| YOU | 8:00 AM | Hit 3 job sites or call 5 contractors. Find tomorrow's jobs NOW. |
| KEYMON | 9:00 AM | Enter all Day 1 workers into tracker. Flag anyone missing forms. |
| YOU | 12:00 PM | Call both contractor supervisors: 'How are the guys doing?' Get feedback. |
| YOU | 2:00 PM | Lock jobs for Day 2. Ask each contractor: 'Same crew tomorrow?' |
| YOU | 3:00 PM | Ask for referrals: 'Anyone else you know who needs reliable workers?' |
| IDRIS | 5:00 PM | Collect or photo time logs from supervisors. |
| KEYMON | 5:30 PM | Enter verified hours into tracker. Flag any without supervisor signature. |
| YOU | 7:00 PM | Send worker availability broadcast for Day 2. |
| YOU | 8:00 PM | Count: jobs confirmed tomorrow vs workers available. Adjust if needed. |

| DAY 2 Tuesday | THEME: REPEAT + EXPAND — LOCK IN RECURRING ACCOUNTS |
| --- | --- |

| WHO | TIME | TASK |
| --- | --- | --- |
| IDRIS | 5:45 AM | Run check-in. Same process. Tighter and faster than Day 1. |
| YOU | 6:30 AM | Confirm returning workers to same contractors. Reinforce the lock-in. |
| IDRIS | 7:00 AM | Dispatch. Any new workers from overnight replies → intake them before assigning. |
| KEYMON | 8:00 AM | Process overnight intake forms. Any new workers need all 3 forms before next dispatch. |
| YOU | 8:00 AM | Field acquisition: 3 new job sites. Introduce NBCA. Collect leads. |
| YOU | 10:00 AM | Call 5 more contractors from your list. Goal: 3 jobs confirmed for Day 3. |
| YOU | 12:00 PM | Midday site check on Day 2 placements. |
| YOU | 2:00 PM | Property manager outreach: call 3 apartment complexes. Use Lever 5 script. |
| KEYMON | 3:00 PM | Update reliability scores from Day 1 feedback. Adjust tiers if needed. |
| YOU | 4:00 PM | Review: how many contractors in your pipeline now? Target: 5 total by end of week. |
| IDRIS | 5:00 PM | Collect time logs. Hand to Keymon. |
| KEYMON | 5:30 PM | Update tracker. Running total of verified hours this week. |
| YOU | 7:00 PM | Worker broadcast for Day 3. Include: trades needed (carpentry/demo/labor). |

| DAY 3 Wednesday | THEME: STACK SMALL JOBS — FILL THE FULL WORKFORCE |
| --- | --- |

| WHO | TIME | TASK |
| --- | --- | --- |
| ALL | 5:45 AM | Full team at NBCA office. Same process. Faster execution. |
| YOU | 6:30 AM | If any new workers from intake — assign to simpler jobs (labor, cleanup). |
| IDRIS | 7:00 AM | Dispatch all confirmed workers. Any gaps in jobs → call Program Lead immediately. |
| YOU | 8:00 AM | Subcontractor outreach: drywall, concrete, roofing crews. 'Short a couple guys?' |
| KEYMON | 9:00 AM | Audit: every worker in system should have all 3 forms signed. Flag any missing. |
| YOU | 11:00 AM | Mid-week review: jobs filled this week, hours logged, contractor feedback. |
| YOU | 1:00 PM | Follow up on every Day 1-2 lead that said 'not now.' 72-hr callback. |
| YOU | 3:00 PM | Lock at least 4 jobs for Day 4. Build buffer so Idris has jobs to fill. |
| KEYMON | 4:00 PM | Prepare weekly hours summary format — will submit Friday. |
| ALL | 5:00 PM | Team huddle (15 min): what's working, what's breaking, what to adjust. |
| YOU | 7:00 PM | Worker broadcast. Note: adjust trade request based on tomorrow's jobs. |

| DAY 4 Thursday | THEME: DEMAND ENGINE ON — ALL 10 LEVERS RUNNING |
| --- | --- |

| WHO | TIME | TASK |
| --- | --- | --- |
| IDRIS | 5:45 AM | Run dispatch. By now this should feel routine. |
| YOU | 8:00 AM | Full field acquisition day. Hit 5+ sites. Carry Job Request Forms. |
| KEYMON | 9:00 AM | Begin preparing BCA hour submission for Friday. Pull all signed logs. |
| YOU | 10:00 AM | Referral sweep: text every contractor who used workers this week. Ask for referrals. |
| YOU | 12:00 PM | Midday check on all active job sites. |
| YOU | 2:00 PM | Review contractor pipeline. Add 3+ new names. Update Demand Pipeline Tracker. |
| KEYMON | 3:00 PM | Cross-check all time logs against dispatch records. Flag any discrepancies. |
| YOU | 5:00 PM | Set Day 5 jobs. Target: same or more than Day 4. |
| YOU | 7:00 PM | Worker broadcast for Friday. |

| DAY 5 Friday | THEME: CLOSE THE WEEK — SUBMIT HOURS — PLAN WEEK 2 |
| --- | --- |

| WHO | TIME | TASK |
| --- | --- | --- |
| IDRIS | 5:45 AM | Run dispatch. Standard process. |
| KEYMON | 9:00 AM | Finalize weekly hours spreadsheet. Verify every entry has supervisor signature. |
| KEYMON | 11:00 AM | Submit verified hours to BCA system. Deadline: 5 PM today. |
| YOU | 10:00 AM | Generate invoices for all contractors whose jobs completed this week (Doc 18). |
| YOU | 12:00 PM | Weekly metrics review: placement rate, hours logged, new contractors, referrals. |
| YOU | 2:00 PM | Brief Br. Hameed: 5-minute update. Numbers, wins, issues, plan for Week 2. |
| KEYMON | 3:00 PM | Update all worker reliability scores for the week. |
| ALL | 4:00 PM | Team debrief: what worked, what to improve, what to automate in the app. |
| YOU | 5:00 PM | Confirm jobs for Monday. Send worker broadcast tonight. |
| KEYMON | 5:00 PM | BCA hour submission confirmed. File all Week 1 documents. |

WEEK 1 SUCCESS CRITERIA

| METRIC | MINIMUM | TARGET |
| --- | --- | --- |
| Workers dispatched (total across week) | 10 | 20+ |
| Jobs filled | 5 | 10+ |
| Verified hours logged | 40 | 100+ |
| BCA funding triggered ($0.77/hr) | $31 | $77+ |
| Contractor accounts active | 2 | 4+ |
| New contractor contacts made | 10 | 25+ |
| Workers fully onboarded (all 3 forms) | 8 | 15+ |
| Referral asks made | 3 | every job |
| Time logs submitted to BCA | 100% | 100% |

IF placement rate drops below 50% two days in a row: pause intake immediately. Do not gather more workers than you have jobs for. Protect the experience.

✓  If you hit the minimum targets by Friday: the system is proven. Week 2 = scale. Add more contractors, more workers, and launch the app.